## Sheet1
EPIC | User Stories
| As a/an | I want to | So That | Acceptance Criteria | Validation | Task List | Story Point | Actual Time | Start Time | End Time | Task Status | Owner | Comments | Scenario 1 (Pass) | Scenario 2 (Fail)
| Admin | 1.1 Login to the portal | to access the portal to make changes and make updates | Username/ email should be of specified format | The username and password should be present in the database | 1. Creating Wireframe(30min) 2. Creating Controller(2hr) 3. Creating dao(1hr) 4. Creating service(1hr) 5. Database connection(1hr) 6. UI design(2hr) 7. Writing test cases(30min) | 1 |  | 2020-10-08 | 22/08/2020 | 1.Done, 2.Done, 3.Done, 4.Done, 5.Done, 6.Done, 7.Done | Siddhant |  | Admin Should provide valid credentials , then he will get successfully Logon. | If Admin does not provides valid credentials , he/she won't abl to access portal
| Admin | 1.2 Add and remove vegetables as per the availability | So that customers can view and buy the available vegetables | Should have a photo | jpg or png type | 1. Creating Wireframe(30min) 2. Creating Controller(2hr) 3. Creating dao(1hr) 4. Creating service(1hr) 5. Database connection(1hr) 6. UI design(2hr) 7. Writing test cases(30min) | 1 |  | 2020-10-08 | 22/08/2020 | 1.Done, 2.Done, 3.Done, 4.Done, 5.Done, 6.Done, 7.Done | Ramya |  | Given the admin has to add/remove vegetables only from edit page. | Admin should not be able to edit items in any page other than the Edit Page.
ONLINE VEGETABLE SALES | Admin | 1.3 Manage Customers/order | Customers can have their issues solved and improve the application | NA | NA | 1. Creating Wireframe(30min) 2. Creating Controller(2hr) 3. Creating dao(1hr) 4. Creating service(1hr) 5. Database connection(1hr) 6. UI design(2hr) 7. Writing test cases(30min) | 1 |  | 2020-10-08 | 22/08/2020 | 1.Done, 2.Done, 3.Done, 4.Done, 5.Done, 6.Done, 7.Done | Ramya |  | Given the admin has to manage customers/orders only from admin edit page. | Admin should not be able to manage customers/orders in any page other than the Edit Page.
| Customer | 2.1 Register to the portal | I can access the portal to get login credentials to explore the website and perform operations on the portal. | Details like name, contact and email should be of a specific format and mandatory field must be filled | Fields entered should be in a proper format should be not be null | 1. Creating Wireframe(30min) 2. Creating Controller(2hr) 3. Creating dao(1hr) 4. Creating service(1hr) 5. Database connection(1hr) 6. UI design(2hr) 7. Writing test cases(30min) | 1 |  | 2020-10-08 | 22/08/2020 | 1.Done, 2.Done, 3.Done, 4.Done, 5.Done, 6.Done, 7.Done | Arjun |  | Given the customer provides the valid details, He will be registered to the portal and will get message registered successfully | Given the customer does not provide the data in proper format , then the customer will not be able to register himself on portal
| Customer | 2.2 Login to the portal | to access the portal to make a purchase | Username/ email should be of specified format | The username and password should be present in the database | 1. Creating Wireframe(30min) 2. Creating Controller(2hr) 3. Creating dao(1hr) 4. Creating service(1hr) 5. Database connection(1hr) 6. UI design(2hr) 7. Writing test cases(30min) | 1 |  | 2020-10-08 | 22/08/2020 | 1.Done, 2.Done, 3.Done, 4.Done, 5.Done, 6.Done, 7.Done | Siddhant |  | Given the customer provides the valid credentials, after logon he will procced to next steps | Given the customer does not provide the data in proper format or given wrong credential, then the customer will not be able to logon himself on portal
| Customer | 2.3 Adding/deleting item from/to cart | So as to buy the products / delete products | NA | Item should be available | 1. Creating Wireframe(30min) 2. Creating Controller(2hr) 3. Creating dao(1hr) 4. Creating service(1hr) 5. Database connection(1hr) 6. UI design(2hr) 7. Writing test cases(30min) | 1 |  | 2020-10-08 | 22/08/2020 | 1.Done, 2.Done, 3.Done, 4.Done, 5.Done, 6.Done, 7.Done | Santosh |  | If customer want to purchase any item, 1st he has to select the items then he can add to cart item or delete from cart | If Customer does not select any item , then he/she unable to adding item to cart or deleting item from cart
| Customer | 2.4 Place Order | so as to buy the product and make payment | Enter the valid address | should enter 16 digit card number, 3 digit CVV | 1. Creating Wireframe(30min) 2. Creating Controller(2hr) 3. Creating dao(1hr) 4. Creating service(1hr) 5. Database connection(1hr) 6. UI design(2hr) 7. Writing test cases(30min) | 1 |  | 2020-10-08 | 22/08/2020 | 1.Done, 2.Done, 3.Done, 4.Done, 5.Done, 6.Done, 7.Done | Priyanka |  | Given the customer provides valid payment details, then he will make successfully payment | Given the customer provides invalid payment details, then he won't be make successfully payment.
| Customer | 2.5 Feedback/Rating | To give feedback to the admin and ask queries | NA | NA | 1. Creating Wireframe(30min) 2. Creating Controller(2hr) 3. Creating dao(1hr) 4. Creating service(1hr) 5. Database connection(1hr) 6. UI design(2hr) 7. Writing test cases(30min) |  |  | 2020-10-08 | 22/08/2020 | 1.Done, 2.Done, 3.Done, 4.Done, 5.Done, 6.Done, 7.Done | Arjun |  | After completing the payment Customer can add his valuable feedback/rating to make our services better. | Customer can also skip this apart as it will be optional.